## TimeTracking
Time Tracking Table
Sum of HOURS | Column Labels
Row Labels | Interface | Presentation | Simulation | Team Meeting | Report | Grand Total
Aris | 2 |  |  | 3 |  | 5
Charlotte |  |  | 15 | 3 |  | 18
Konstantinos |  |  | 2 | 3 |  | 5
Panagiotis |  | 3 | 3 | 3 | 3 | 12
Zerin |  | 2 |  | 3 |  | 5
Grand Total | 2 | 5 | 20 | 15 | 3 | 45

## DATA
NAME | HOURS | JOB DESCRIPTION | DATE | DETAILS
Panagiotis | 2 | Team Meeting | 2024-01-10 | Discussed how we gonna split the workload, approaches we will make to our problem
Aris | 2 | Team Meeting | 2024-01-10
Konstantinos | 2 | Team Meeting | 2024-01-10
Zerin | 2 | Team Meeting | 2024-01-10
Charlotte | 2 | Team Meeting | 2024-01-10
Panagiotis | 2 | Presentation | 2024-01-10 | Presentation for Thursday 11/01/24
Zerin | 2 | Presentation | 2024-01-10
Aris | 2 | Interface | 2024-01-10
Charlotte | 4 | Simulation | 2024-01-10 | discussed a game plan on how to approach the situation and wrote the functions to get the information to make the class eldery
Konstantinos | 2 | Simulation | 2024-01-10
Panagiotis | 1 | Presentation | 2024-01-10 | Preparing Presentation for Thursday
Panagiotis | 1 | Team Meeting | 2024-01-11
Aris | 1 | Team Meeting | 2024-01-11
Konstantinos | 1 | Team Meeting | 2024-01-11
Zerin | 1 | Team Meeting | 2024-01-11
Charlotte | 1 | Team Meeting | 2024-01-11
Charlotte | 4 | Simulation | 2024-01-11 | Finished simulation for both queues
Panagiotis | 2 | Simulation | 2024-01-11 | Adds-on(Shared beds)
Panagiotis | 1 | Report | 2024-01-11 | Start with the structure of the report, have a basic idea what we will write about
Charlotte | 6 | Simulation | 2024-01-12 | Corrected mistakes in simulation, and added some parameters, and graphs
Charlotte | 1 | Simulation | 2024-01-13
Panagiotis | 1 | Simulation | 2024-01-14 | Adds-on(Shared beds)
Charlotte | 5 | Simulation | 2024-01-15 | Changed simulations
Panagiotis | 2 | Report | 2024-01-15 | Finallizing the project plan
Panagiotis | 2 | Team Meeting | 2024-01-16 | Meeting with our supervisor to discuss about our progress and issues we are facing
Aris | 2 | Team Meeting | 2024-01-16
Konstantinos | 2 | Team Meeting | 2024-01-16
Zerin | 2 | Team Meeting | 2024-01-16
Charlotte | 2 | Team Meeting | 2024-01-16