## TimeTracking
Time Tracking Table
Sum of HOURS | Column Labels
Row Labels | Interface | Simulation | Team Meeting | Presentation\Report | Grand Total
Aris | 36 | 2 | 13 | 2 | 53
Charlotte |  | 44 | 11 | 2 | 57
Konstantinos |  | 14 | 13 | 5 | 32
Panagiotis |  | 23 | 13 | 20 | 56
Zerin | 26 |  | 13 | 10 | 49
Grand Total | 62 | 83 | 63 | 39 | 247

## DATA
NAME | HOURS | JOB DESCRIPTION | DATE | DETAILS
Panagiotis | 2 | Team Meeting | 2024-01-10 | Discussed how we gonna split the workload, approaches we will make to our problem
Aris | 2 | Team Meeting | 2024-01-10
Konstantinos | 2 | Team Meeting | 2024-01-10
Zerin | 2 | Team Meeting | 2024-01-10
Charlotte | 2 | Team Meeting | 2024-01-10
Panagiotis | 2 | Presentation\Report | 2024-01-10 | Presentation for Thursday 11/01/24
Zerin | 2 | Presentation\Report | 2024-01-10
Aris | 3 | Interface | 2024-01-10
Zerin | 2 | Interface | 2024-01-10
Charlotte | 4 | Simulation | 2024-01-10 | discussed a game plan on how to approach the situation and wrote the functions to get the information to make the class eldery
Konstantinos | 2 | Simulation | 2024-01-10
Panagiotis | 1 | Presentation\Report | 2024-01-10 | Preparing Presentation for Thursday
Panagiotis | 1 | Team Meeting | 2024-01-11
Aris | 1 | Team Meeting | 2024-01-11
Konstantinos | 1 | Team Meeting | 2024-01-11
Zerin | 1 | Team Meeting | 2024-01-11
Charlotte | 1 | Team Meeting | 2024-01-11
Charlotte | 4 | Simulation | 2024-01-11 | Finished simulation for both queues
Panagiotis | 2 | Simulation | 2024-01-11 | Adds-on(Shared beds)
Panagiotis | 1 | Presentation\Report | 2024-01-11 | Start with the structure of the report, have a basic idea what we will write about
Zerin | 2 | Interface | 2024-01-12
Charlotte | 6 | Simulation | 2024-01-12 | Corrected mistakes in simulation, and added some parameters, and graphs
Charlotte | 1 | Simulation | 2024-01-13
Aris | 2 | Interface | 2024-01-14
Zerin | 2 | Interface | 2024-01-14
Panagiotis | 1 | Simulation | 2024-01-14 | Adds-on(Shared beds)
Charlotte | 5 | Simulation | 2024-01-15 | Changed simulations
Aris | 3 | Interface | 2024-01-15
Panagiotis | 2 | Presentation\Report | 2024-01-15 | Finallizing the project plan
Panagiotis | 2 | Team Meeting | 2024-01-16 | Meeting with our supervisor to discuss about our progress and issues we are facing
Aris | 2 | Team Meeting | 2024-01-16
Konstantinos | 2 | Team Meeting | 2024-01-16
Zerin | 2 | Team Meeting | 2024-01-16
Charlotte | 2 | Team Meeting | 2024-01-16
Aris | 4 | Interface | 2024-01-16
Panagiotis | 3 | Presentation\Report | 2024-01-16 | Project plan and Final report
Panagiotis | 1 | Simulation | 2024-01-16 | Starting with the sensitivity analysis
Charlotte | 4 | Simulation | 2024-01-16
Zerin | 1 | Presentation\Report | 2024-01-17
Aris | 2 | Interface | 2024-01-17
Panagiotis | 6 | Simulation | 2024-01-17 | Sensitivity analysis about the amount of beds-shared beds
Panagiotis | 3 | Simulation | 2024-01-18
Panagiotis | 1 | Simulation | 2024-01-19
Aris | 4 | Interface | 2024-01-18
Zerin | 4 | Interface | 2024-01-18
Charlotte | 3 | Simulation | 2024-01-18
Charlotte | 3 | Simulation | 2024-01-19 | adds - on decentralisation
Aris | 4 | Interface | 2024-01-19
Zerin | 4 | Interface | 2024-01-19
Konstantinos | 4 | Simulation | 2024-01-20 | Optimization of solutions
Konstantinos | 4 | Simulation | 2024-01-21
Panagiotis | 1 | Presentation\Report | 2024-01-21
Zerin | 2 | Interface | 2024-01-21
Panagiotis | 2 | Team Meeting | 2024-01-22 | Zoom Meeting to discuss our progress and work on the presentation for Thursday
Aris | 2 | Team Meeting | 2024-01-22
Konstantinos | 2 | Team Meeting | 2024-01-22
Zerin | 2 | Team Meeting | 2024-01-22
Charlotte | 2 | Team Meeting | 2024-01-22
Aris | 2 | Interface | 2024-01-22
Panagiotis | 3 | Presentation\Report | 2024-01-23
Zerin | 3 | Presentation\Report | 2024-01-23
Charlotte | 1 | Presentation\Report | 2024-01-22
Charlotte | 2 | Simulation | 2024-01-20 | Fix little things in code
Charlotte | 1 | Presentation\Report | 2024-01-23 | Made the picture that shows are queue
Panagiotis | 1 | Simulation | 2024-01-24
Panagiotis | 3 | Presentation\Report | 2024-01-24
Charlotte | 6 | Simulation | 2024-01-25 | checking what should basic settings/ decentralisation/ getting info for confidence interval
Panagiotis | 3 | Simulation | 2024-01-25
Aris | 2 | Simulation | 2024-01-25
Panagiotis | 2 | Team Meeting | 2024-01-25
Aris | 2 | Team Meeting | 2024-01-25
Konstantinos | 2 | Team Meeting | 2024-01-25
Zerin | 2 | Team Meeting | 2024-01-25
Panagiotis | 2 | Team Meeting | 2024-01-26
Aris | 2 | Team Meeting | 2024-01-26
Konstantinos | 2 | Team Meeting | 2024-01-26
Zerin | 2 | Team Meeting | 2024-01-26
Charlotte | 2 | Team Meeting | 2024-01-26
Charlotte | 6 | Simulation | 2024-01-26 | Fixen stuff, graphs,
Aris | 4 | Interface | 2024-01-26
Panagiotis | 4 | Simulation | 2024-01-26
Konstantinos | 3 | Simulation | 2024-01-26
Zerin | 4 | Interface | 2024-01-26
Konstantinos | 3 | Presentation\Report | 2024-01-27
Panagiotis | 1 | Presentation\Report | 2024-01-27
Zerin | 3 | Presentation\Report | 2024-01-27
Aris | 2 | Presentation\Report | 2024-01-27
Panagiotis | 1 | Presentation\Report | 2024-01-28
Zerin | 3 | Interface | 2024-01-28
Aris | 4 | Interface | 2024-01-28
Panagiotis | 2 | Team Meeting | 2024-01-29
Aris | 2 | Team Meeting | 2024-01-29
Konstantinos | 2 | Team Meeting | 2024-01-29
Zerin | 2 | Team Meeting | 2024-01-29
Charlotte | 2 | Team Meeting | 2024-01-29
Panagiotis | 1 | Simulation | 2024-01-29
Panagiotis | 2 | Presentation\Report | 2024-01-29
Zerin | 1 | Presentation\Report | 2024-01-29
Zerin | 3 | Interface | 2024-01-29
Konstantinos | 1 | Simulation | 2024-01-29
Konstantinos | 2 | Presentation\Report | 2024-01-29
Aris | 4 | Interface | 2024-01-29
Charlotte | 8 | Simulation | 2024-01-29 | verification